## Tareas
ID | Categoria | Descripcion | Estado | Asignado | Requiere Evidencia | ID Tarea
1305 | Desmalezadores | Zanja las calandrias zona 1 | Done | Alexis Vega | NO | 1
1306 | Desmalezadores | Zanja las calandrias zona 2 | Done | Alexis Vega | NO | 2
1307 | Desmalezadores | Zanja las perdices zona 1 | Done | Alexis Vega | NO | 3
1308 | Desmalezadores | Zanja las perdices zona 2 | Done | Alexis Vega | NO | 4
1309 | Desmalezadores | Zanja los buhos zona 1 | Not started |  | NO | 5
1310 | Desmalezadores | Zanja los buhos zona 2 | In progress | Alexis Vega | NO | 6
1311 | Desmalezadores | Zanja los colibries zona 1 | In progress | Alexis Vega | NO | 7
1312 | Desmalezadores | Zanja los colibries zona 2 | In progress | Alexis Vega | NO | 8
1313 | Desmalezadores | Cantero Avenida zona 2 | Not started |  | NO | 9
1314 | Desmalezadores | Zanjas Avenida zona 2 | Not started |  | NO | 10
1315 | Desmalezadores | Zona Lago parte interna | Not started |  | NO | 11
1316 | Desmalezadores | Zona Lago parte perimetral | Not started |  | NO | 12
1317 | Desmalezadores | Cantero Avenida zona 1 | Not started |  | NO | 13
1318 | Desmalezadores | Zanjas Avenida zona 1 | Not started |  | NO | 14
1319 | Desmalezadores | Lote 164 | Not started |  | NO | 15
1320 | Desmalezadores | Zanjas los cardenales | Not started |  | NO | 16
1321 | Desmalezadores | Zanjas los horneros | Not started |  | NO | 17
1322 | Desmalezadores | Lote 149 | Not started |  | NO | 18
1323 | Desmalezadores | Lote 45 | Not started |  | NO | 19
1324 | Desmalezadores | Ingreso | Not started |  | NO | 20
1358 | Desmalezadores | Pueden cortar el lote 129, el vecino les paga 20mil a cada uno | Pending approval |  | SI
1359 | Desmalezadores | Cortar lote 148, el vecino les paga aparte 20 mil a cada uno | Pending approval |  | SI
1325 | Tractor | Zona Eucaliptos | Not started |  | NO | 21
1326 | Tractor | Manzana 2 | Not started |  | NO | 22
1327 | Tractor | Manzana 3 | Not started |  | NO | 23
1328 | Tractor | Manzana 4 | Not started |  | NO | 24
1329 | Tractor | Manzana 5 | Not started |  | NO | 25
1330 | Tractor | Manzana 8 | Not started |  | NO | 26
1331 | Tractor | Manzana 6 | Not started |  | NO | 27
1332 | Tractor | Zona Lago | Not started |  | NO | 28
1333 | Tractor | Manzana 7 | Not started |  | NO | 29
1334 | Tractor | Manzana 1 | Not started |  | NO | 30
1335 | Tractor | Zona Ruta | Not started |  | NO | 31
1336 | MiniTractor | Lote 229 | Done | Gabriel | NO | 32
1337 | MiniTractor | Lotes arbol en el centro | Done | Gabriel | NO | 33
1338 | MiniTractor | Club House | Done | Gabriel | NO | 34
1339 | MiniTractor | Zanja calle ingreso | Done | Gabriel | NO | 35
1340 | MiniTractor | Zanja los colibries zona 1 | In progress | Gabriel | NO | 36
1341 | MiniTractor | Zona Casita madera | In progress | Gabriel | NO | 37
1342 | MiniTractor | Zanja los buhos zona 1 | Not started |  | NO | 38
1343 | MiniTractor | Lote 119 | In progress | Gabriel | NO | 39
1344 | MiniTractor | Lote 310 | In progress | Gabriel | NO | 40
1345 | MiniTractor | Lote 130 | Not started |  | NO | 41
1346 | MiniTractor | Lote 134 | Not started |  | NO | 42
1347 | MiniTractor | Zanjas los cardenales | Not started |  | NO | 43
1348 | MiniTractor | Zanjas los horneros | Not started |  | NO | 44
1349 | MiniTractor | Lote 164 | Not started |  | NO | 45
1350 | MiniTractor | Zanja las perdices zona 1 | Not started |  | NO | 46
1351 | MiniTractor | Zanjas Avenida zona 1 | Not started |  | NO | 47
1352 | MiniTractor | Cancha Futbol | Not started |  | NO | 48
1353 | MiniTractor | Lote 83 | Not started |  | NO | 49
1354 | Pileta | Tirar ácido en pileta | Done | Gabriel | NO | 50
1355 | Pileta | Revisar cloro tanques de agua | Pending evidence | Gabriel | SI | 51
1356 | Barre fondo | Pasar barre fondo | Done | Gabriel | NO | 52
1357 | Barre fondo | Pasar barre fondo | Not started |  | NO | 53

## Dias Laborales
Categoria | Lunes | Martes | Miercoles | Jueves | Viernes | Sabado | Domingo
Desmalezadores
Tractor
MiniTractor
Pileta
Barre fondo